# BDSH Advisor Meeting Minutes

| DATE: 26/08/26 | TIME: 11:00AM |
| --- | --- |
| LOCATION: T7 Meeting room |  |
| ATTENDEES: Clement Swarnappa, Dave Sushames, Matt Baker, Olivia Hey, Sam Davies |  |
| APOLOGIES: N/A | NON-ATTENDEE(S): N/A |
| MEETING LEADER: Olivia Hey | MINUTES TAKER: Dave Sushames |

PROJECT NAME: AI - Augmented vs Legacy Digital Forensics Tools – A Comparative Efficacy Analysis

PROJECT PURPOSE: Provide an empirical analysis on Ai-augmented digital forensics technologies

MEETING PURPOSE: Update Clement on the status of the project and team

| AGENDA ITEM: | LED BY (Initials Only): | TIME ALLOTTED: |
| --- | --- | --- |
| Inclusion of Bryce Antony as technical advisor, where he fits into this project, his expertise etc. | OH | 10 |
| Change of role, types of activities Dave can perform without great technical understanding (human tester? Test case writing?) | DS | 5 |
| State of the project, change of PM, change of methodology, thoughts. | OH | 10 |
| Discuss a time of meeting change after this week going forward | OH | 5 |
| Discuss new methodology (design science) | OH | 5 |
| Strategies on increasing hours, 40 per week? | MB | 5 |
| Discuss latest version of proposal | MB | 10 |
| Discuss opportunities for potential milestones | DS | 10 |

| ACTION ITEM: | DELIVERABLE(S): |
| --- | --- |

MEETING NOTES:

1105 Catch up. It’s not about how far behind other teams we are, some teams just start slow. 1110 Olivia explains Bryce’s position as technical advisor. Clement says advisors are really there to step in when needed, he doesn’t need to check everything all the time. We talk about what we’ve been doing. 1115 We have to format the data in such a way that the AI can read it. Matt is the “technical expert” who can teach others how to do this? 1120 Design science is so that Bryce can see/track how we’re doing. All methodologies work kind of, at least 70%. So a “perfect methodology” for a situation is only 30% better than any other one. Just go with what you’re familiar with. Tool > Data > AI > Output/artifact. Discuss how the project has changed, from AI equivalent tools, to AI reports. Confusion over “efficacy”. 1125 How to test speed/accuracy/consistency? How to apply the tools? Bryce has something for Nmap. 1130 “AI tools” were just an AI using the legacy tool, not anything special. Future meetings: Mon or Wed ideal for Clement. Ask on the Friday about the following week. 1135 We need more hours. Allow time for learning. Research, test out tools, have regular meetings. 1140 We lack client milestones. Own it. Keep Geoff updated. Maybe have a client demo of how we’re doing every couple weeks. Project management methodology. Can probably have ~50 hours each just researching Design Science, figuring out what types of artifacts we need. 1145 Kanban boards can be used for other things than just project management. Ideally for a monitoring tool. Meeting ended at 1200.

| DETAILS OF NEXT MEETING: |  |
| --- | --- |
| DATE: N/A | TIME: N/A |
| LOCATION: T7 Meeting room |  |
| MEETING CLOSED: 12pm |  |

SIGNATURES

| Name: Clement Swarnappa | Role: Advisor | Signature: |
| --- | --- | --- |
| Name: Olivia Hey | Role: Project Manager | Signature: Olivia Hey |
| Name: Matt Baker | Role: Digital Forensics Technician | Signature: Matt Baker |
| Name: Sam Davies | Role: Digital Forensics Technician | Signature: Sam Davies |
| Name: Dave Sushames | Role: Tester | Signature: Dave Sushames |