# BDSH Advisor Meeting Minutes

| DATE: 29/07/26 | TIME: 1:00pm |
| --- | --- |
| LOCATION: T706 |  |
| ATTENDEES: Clement Swarnappa, Dave Sushames, Matt Baker, Olivia Hey, Sam Davies |  |
| APOLOGIES: N/A | NON-ATTENDEE(S): N/A |
| MEETING LEADER: Dave Sushames, Matt Baker | MINUTES TAKER: Olivia Hey |

PROJECT NAME: AI vs Legacy Digital Forensics Tools – A Comparative Efficacy Analysis

PROJECT PURPOSE: Provide an empirical analysis on AI digital forensics technologies

MEETING PURPOSE: Meet with our Advisor for the first time and discuss our project so far

| AGENDA ITEM: | LED BY (Initials Only): | TIME ALLOTTED: |
| --- | --- | --- |
| Tell Clement about the project | MB | 5m |
| Discuss final project outcomes | DS | 10m |
| Discuss producing the proposal and Clement’s role as an advisor | DS | 10m |
| Discuss project methodologies and advice on what we should do | DS | 15m |
| Discuss github as a repo | DS | 5m |
| Additional questions | N/A | N/A |
| Assigning next meeting date and time (12pm Thursday) |  |  |

| ACTION ITEM: | DELIVERABLE(S): |
| --- | --- |
| Dave needs to make a repository | GitHub repository / One drive repo |
| Dave organises project for the next few weeks | Gantt chart + work breakdown structure |

MEETING NOTES:

Final project outcome - Report isn’t enough - Suggests we talk to Geoff about the final outcome and what he expects to get out of it - Suggests we ask a lot of questions - Research and create proposal to Geoff so we can discuss requirements Research different project methodologies - Dave make a gantt chart on Microsoft project - Gantt chart is a live document - We should begin with a WBS and network (?) and then do the gantt chart so it is optimized - Is a dynamic document Github isn’t exclusive to programming, can upload any files - Research how to use github for storing our data and document changes - How to use git for our proposal? - Reiterates research Dave needs to reply to emails - Have a meeting with Geoff next week and draft 1 of proposal by Thursday 12 next week to go over with Clement next week - Produce work output of hours you do - Recommends AI to sort research topics - Dave build an agenda for meetings and send the notes to Clement beforehand. Ends at 2pm

| DETAILS OF NEXT MEETING: 12pm Thursday with Clement to look over Proposal draft. |  |
| --- | --- |
| DATE: 6/8/26 | TIME: 12pm |
| LOCATION: T706 |  |
| MEETING CLOSED: 2pm |  |

SIGNATURES

| Name: Clement Swarnappa | Role: Advisor | Signature: |
| --- | --- | --- |
| Name: Dave Sushames | Role: Project Manager | Signature: Dave Sushames |
| Name: Matt Baker | Role: Digital Forensics Technician | Signature: Matt Baker |
| Name: Sam Davies | Role: Digital Forensics Technician | Signature: Sam Davies |
| Name: Olivia Hey | Role: Digital Forensics Technician | Signature: Olivia Hey |